## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2022-04-04
Group Number |  | 2
Participant 1 |  | Schneider Brian
Participant 2 |  | Alexander Berg
Participant 3 |  | Simon Rutschka
Participant 4 |  | Josua Hämmerle
Participant 5 |  | Wunsch Lukas
Mentor |  | Parg Manuel-Christopher
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Spielkonzept fixieren | 20 | 22 | 2 | 1
2 | Backlog erstellen | 5 | 5 | 0 | 1
3 | Arbeitsteilung | 5 | 5 | 0 | 1
4 | Tools aufsetzen | 10 | 15 | 5 | 1
5 | Meeting mit Coach | 2.5 | 1 | -1.5 | 1
6 | Unity lernen | 5 | 3 | -2 | 1
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 3.5 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol