## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2022-06-18
Group Number |  | 2
Participant 1 |  | Berg Alexander
Participant 2 |  | Hämmerle Josua
Participant 3 |  | Schneider Brian
Participant 4 |  | Rutschka Simon
Participant 5 |  | Wunsch Lukas
Mentor |  | Parg Manuel-Christopher
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Meeting 16.06 | 5 | 10 | 5 | 1 |  | Arbeitsteilung Sprint 6
2 | Shop/Geldsystem | 12 | 10 | -2 | 1
4 | Enemy Typen | 25 | 20 | -5 | 1
5 | Wavespawning fertig stellen | 15 | 15 | 0 | 1
6 | HUD | 15 | 15 | 0 | 1
7 | Damagesystem | 20 | 20 | 0 | 1
8 | Musik/Soundeffekte | 10 | 15 | 5 | 1
9 | Meeting 19.06 | 5 | 10 | 5 |  |  | Code zusammenfügen, Testen, Bugfix
10 | Meeting 20.06 | 5 | 1 | -4 | 1
9 |  |  | 116 | 4 | 8 | 0